## 2019
PROJECT | PRIORITY LEVEL | DESCRIPTION | Status
2020 BUDGET | HIGH | Preparing Budget for Discussion | COMPLETE
MASTER PLAN | HIGH | Update the Master Plan / Separate from Joint Master Plan | 2020
PARKS & RECREATION PLAN | HIGH | Sub-committee continues to update P&R Plan. | IN PROGRESS
PARKS & REC ORDINANCE | HIGH | Using sub-committee of the PC to review plan. P&R Ordinance initiative retracted. | INITIATIVE RETRACTED
VEHICLE PURCHASE | HIGH | Utility vehicle is now in service. | COMPLETE
VEHICLE PURCHASE #2 | HIGH | Ford Fleet # applied for as required for discounted rate. UPDATE: 11-12-19 Purchase Agreement being drafted for consideration. New vendor being utilized / former vendor no longer being used. | IN PROGRESS
DIRECTOR OF FACILITIES | HIGH | A position that is a high priority for Village Council - Advertised in MWEA / MML- Hired. | COMPLETE
BEACH STREET PUMPS | HIGH | This item has gone from a medium/low priority to High priority due to a pump failure. Cost before VC for consideration to purchase 2 new pumps and one set of VFD's. UPDATE: Upon discussion with electrician VFD is readily available. No purchase of VFD was made. Update: Pump drawdown test mid-July data stored. Cost of pumps came from funds previously allocated to canceled project. | COMPLETE
CROSS CONNECTION ORDINANCE | HIGH | MDEQ REQUIREMENT | F&V
LEAD & COPPER MATERIALS INVENTORY | HIGH | MDEQ REQUIREMENT - PRELIMINARY DISTRIBUTION SYSTEM MATERIALS INVENTORY (DSMI) DUE JANUARY 1, 2020 | COMPLETE
PORT SUTTONS LIFT STATION | HIGH | Construct new lift station to service PS and Bay View. Bids Received cost too high at $568,000 with $350,000 budgeted. UPDATE:- Cancelled project due to lack of need. | PROJECT CANCELED
EMPLOYEES MANUAL | HIGH | Proposal before VC 9-16-19. UPDATE: 11-21-19 Rough Draft Received. | IN PROGRESS
TAP GRANT - DETOUR AMENDMENT | HIGH | Change TAP grant detour to 4th street update- Postponed following Pre-con meeting. | COMPLETE
MARINA - EMERGENCY REPAIRS | HIGH | High water erosion issues. - Meeting with the Engineer and State on 6-10-19 - UPDATE: requires additional permitting per Robyn. F&V working on this. UPDATE: Permit Received. | COMPLETE
CONSUMERS CONTRACTS | HIGH | Are resolutions needed? UPDATE: to be discussed at September Utility Committee Meeting. | IDLE
CROSS CONNECTION TRAINING | HIGH | Staff Training Required | IDLE
WWTP - LINER & BAFFLE REPLACEMENT | HIGH | Maintenance Item ordered as a cost savings to replace baffles during liner replacement. | COMPLETE
PUBLIC / MARINA RESTROOM UPGRADES | HIGH | The structure appears to have or currently is settling causing structural damage. Engineer to evaluate the structures integrity and offer solutions. UPDATE: Engineer meeting scheduled for September 9th. | COMPLETE
BROADWAY ROAD DRAINAGE | HIGH | Drainage overflow from private property causing secondary issues. UPDATE: field visits confirm private basin is the issue causing down street erosion and possible flooding. Discussed with LCRC. UPDATE: LCRC was sent an email based on memo stating it was installed by the LCRC awaiting response. UPDATE: Verbal provided by LCRC superintendent with no memory or information, including plan sets for the road. UPDATE: 10-1-19 Searching permits at County level. UPDATE:10-7-19 Dave and I met with LCRC manager to discuss various items mostly collaboration. 11-22-19 Met with Drain Commissioner/SB Township Supervisor on issue. Drainage district proposed for consideration to fix lack of culverts, ditching. etc. Further research by DC forthcoming. | IN PROGRESS
FACILITIES PHONE UPGRADE | HIGH | Current phones dated and costly. New phones provided through government first responder initiative at less cost with benefits. | COMPLETE
MARINA PROJECT- Overall Project | HIGH | CONSTRUCTION PROGRESSING - BEHIND SCHEDULE - UPDATE- Walkthrough completed 7-16-19. UPDATE: Received an email with checklist of remaining items to be completed on 9-19-19. October 15 completion date. UPDATE: 10-29-19 - The Marina project is approximately 90% complete.UPDATE: 11-27-19 Met with engineer to finalize contract cost. | 90% COMPLETE
MARINA PROJECT - Weggener - Electrician | HIGH | UPDATE: 11-27-19 Met with Waggoner Electric to finalize contract overture cost. Deal negotiated - complete. | COMPLETE
MARINA PROJECT - Engineer | HIGH | UPDATE: 11-26-19 Met with project engineer to finalize contract overture. Deal negotiated | COMPLETE
MARINA SEICHE POND | HIGH | Met with Leelanau County Soil Erosion regarding new sand and ponding. Update - Met with Robyn (EGLE) regarding the seiche pond - Contacted the Army Corp regarding both. - Working with corp- Both County & EGLE have no issues. UPDATE: Topo in place. UPDATE: 4 dates provided in which the emergency manager, was contacted due to threats to our marina infrastructure.(7-22/7-23/7-25/7-29) | COMPLETE
WEBSITE | HIGH | ONGOING - Dorothy constructing site with assistance from LIAA.Website is up and running! | COMPLETE
TAP PROJECT | HIGH | Ongoing Discussions with Engineer / STATUS UNKNOWN - UPDATE - Walkthrough scheduled 7-17-19 UPDATE: Pre-con being scheduled. UPDATE: Postponed UPDATE: 11-25-19 - Still postponed until Spring. | POSTPONED
OFFICE ASSISTANCE | HIGH | A position that is a high priority. | COMPLETE
ARCHITECT - ADA COMPLIANT DECK | HIGH | Funding retracted by committee. All involved have been notified that project is a no go. | INITIATIVE RETRACTED
STREET EVALUATION SOUTH SHORE | HIGH | Evaluation of S. Shore "hump" has been requested. Apparently the hump is a result of a stream culvert? | 2020
VILLAGE STREET - WEIGHT LIMITS | HIGH | Vehicles with excess weight damaging Village Streets. Weight limits on numerous roadways including Elm to circumvent unnecessary weight and short cuts by semi-trucks. UPDATE: 9/19 Meeting scheduled with LCRC. | IDLE
STREET EVALUATION - ELM STREET | HIGH | STREET REPAIR TO BE EVALUATED. UPDATE: Meeting with LCRC 10-7-19 to discuss the roadway. A very good meeting with the manager. Looking forward to further collaboration on this item as well as others. Update: Village is not eligible for consideration for federal $$$ (Ruiral Task Force) until 2022-23. | IN PROGRESS
WATERWHEEL PARK | MEDIUM / HIGH | Creek restoration, waterwheel upgrade, wall replacement, etc. UPDATE: Ongoing conversations with Watershed Center - -No action as of yet - Seeking other avenues. UPDATE: Engineer review complete. Discussion on validity of bids received in 2018 needs discussion. | ENGINEER EVALUATION COMPLETE
PLANNING COMMISSION BY LAW UPDATE | MEDIUM / HIGH | Review and amend bylaws to understand roles & responsibilities, the reason they are on PC, why decisions are made and personal conduct. UPDATE; 10-2-19 Complete | COMPLETE
VILLAGE ATTIRE | MEDIUM / HIGH | All workers in the field to have logo's/uniforms. 11-22-19 Four recently purchased work jackets have been taken in for logos. More to come. | COMPLETE
PLOW TRUCK | MEDIUM / HIGH | Plow truck was taken in July -received in November. 11-20-19- Inspection of brakes showed maintenance neglect. Leaf spring broken badly needs replaced. | COMPLETE
VILLAGE HALL LANDSCAPE | MEDIUM / HIGH | A 2019 budgeted item with high importance to VC. UPDATE: 10-7-19 Contract signed irrigation/landscape to be installed within 3-4 weeks. UPDATE: 10-24-19 Complete/Winterized 10-25-19. | COMPLETE
MARINA BRIDGE REPLACEMENT | MEDIUM / HIGH | The bridge is increasingly becoming aged. Incorporate it into a CMG grant with shoreline protection. Discussed with Engineer and MDEQ - 6-5-19 | IDLE
WATER RESERVOIR EXPANSION | MEDIUM / HIGH | Per MDEQ additional water storage is REQUIRED - this item was recommended by the MDEQ in 2018. UPDATE: F&V reviewing financials and eligibility for granting opportunities. UPDATE: Met with F&V to discuss expansion initiative. 40 year loan @ 2.5%(ish) on $2.5 million loan would cover line upgrade northern loop, reservoir, and 2 new wells. Next steps forthcoming. See rate note below. | IN PROGRESS
WATER RATES | MEDIUM / HIGH | EVALUATION OF WATER RATES UPDATE: F&V UPDATE: Reviewing UPDATE: Met with F&V to discuss expansion initiative. RATES would see less than $4.00 / month increase for reservoir expansion etc. listed above to cover that project for life of loan. | IN PROGRESS
WATER LICENSE | MEDIUM / HIGH | Per MDEQ additional water license of S3 required in less than 150 users. This item has been recommended by the MDEQ in 2018, new hire is qualified. | COMPLETE
BLIGHT ORDINANCE | MEDIUM / HIGH | Pre-Draft provided to General Committee at the September 3rd meeting to determine support for the initiative. Recommendation was to move forward with close attention to ornament grass. UPDATE: 10-28-196 sent to the Attorney for review/comment. | IN PROGRESS
LAND DIVISION ORDINANCE | MEDIUM / HIGH | This Ordinance is antiquated and should be simplified. | IN PROGRESS
PRIVATE ROAD ORDINANCE | MEDIUM / HIGH | Standards in the zoning ordinance are antiquated and should be revised to allow flexibility and to regulate the roads by number of users rather than length. | IN PROGRESS
INLAND SEAS LEASE AGREEMENT | MEDIUM / HIGH | 6-6-19 provided comments in email following meeting / discussions with Inland Seas - UPDATE; INLAND SEAS TO HAVE ATTORNEY DRAFT A LEASE AGREEMENT. UPDATE: 11-21-19 Draft Lease agreement received, being reviewed for content and will provide comments on the lease. | IN PROGRESS
BROADBAND AVAILABILITY | MEDIUM / HIGH | GTB is running broadband to the Suttons Bay Schools and through the Village. Discussions on extending the Broadband to the Village Hall (and other municipalities) was positive. | IN PROGRESS
METRO ACT PERMIT | MEDIUM / HIGH | Went before the committee in September and was recommended for approval to VC September 16th. UPDATE: Permit issued and mailed to the State as required. | COMPLETE
DUESTER PARK UPGRADES | MEDIUM / HIGH | Clean out and reclaim restrooms. Paul did a great job leading the project and personally re-plumbed the bathrooms. | COMPLETE
NORTH PARK BATHROOM UPGRADE | MEDIUM / HIGH | Replace faucets with "timed" faucets and replace counters. Both faucets broken and counters rotted. | IN PROGRESS
MARINA - COAL DOCK | MEDIUM / HIGH | Armoring Coal Dock Side - Changes needed to plans to account for high water. - Permits issued - UPDATE: Move to 2020. UPDATE: Contract signed with Elmer's 10-23-19 to move forward with Fall 2019 project. | COMPLETE
PORT SUTTONS GENERATORS | MEDIUM / HIGH | Quotes received for permanent generators. Budget allows for purchase. Generators will supplement (1) Lift Station & (1) Water well house. UPDATE: 9-19 Funding in place to purchase prior to the budget year. UPDATE - Signed purchase agreement 11-20-19. Awaiting installation, typically a 60-90 day timeframe. | COMPLETE
WATER WELL PROTECTION PROGRAM | MEDIUM / HIGH | Recommended by MDEQ to update / redraft well protection - This item has been recommended by the MDEQ in 2018 UPDATE: 10-08-19 We received notice today that our grant application was accepted by EGLE. Formal paperwork forthcoming. | IN PROGRESS
VILLAGE WATER ORDINANCE | MEDIUM / HIGH | This item has been recommended by the MDEQ in 2018 - Ordinance dated needs attention - F&V to review and provide direction. Contract needed | INITIATED
WATER ORDINANCE INTERPRETATION | MEDIUM / HIGH | Amend ordinance to incorporate interpretation / policy approved by VC. UPDATE - Engineer review prior to amendment. UPDATE: Policy/interpretation rescinded 7-15-19 VC Mtg. | COMPLETE
VILLAGE LOGO | MEDIUM / HIGH | New logo that better fits the Village. | COMPLETE
GPS SERVICES | MEDIUM | There have been several discussion with the vendor working towards a free 30-60 day unit and service. - Wil meet in fall to continue discussions. - UPDATE: Trial period accepted by vendor. BUDGET 2020 | IN PROGRESS
MSU EXTENSION PARTNERSHIP | MEDIUM | Master Gardener Coordinator for MSU Extension in Leelanau County. Discussions to explore the possibility of expanding into the village. Several Master Gardener Volunteers living within the village limits or in the vicinity and there is a lot of potential for collaboration on public garden-related projects. 2020 Project | INITIATED
JEFFERSON STREET PEDESTRIAN COURT | MEDIUM | Temporary Closure for pedestrian use? UPDATE: Move to 2020 following discussions with businesses and VC. NEW location to be proposed. | IDLE
PEDESTRIAN SEATING AREAS DOWNTOWN | MEDIUM | $8,000 Allocated to downtown furniture and bike racks for pedestrian comfort. This will follow an evaluation of the finalized TAP project to determine locations. | IDLE
PAVING PROJECT PARK WALKWAY | MEDIUM | South Shore/Suttons Park - create pedestrian circulation, reclaim park from parking area. Angle 20-23 ft. UPDATE: Elmer's proposal recommended to Village Council. UPDATE: Proposal signed - awaiting timing of project. | INITIATED
CHARTER CABLE EXTENSION DPW | MEDIUM | Discussions with Charter on expanding service to the DPW to properly service the WWTP, offices, etc. UPDATE: Charter measured distance 9-19. waiting on cost and timeframe. | CONTRACT COMPLETE
DPW/WWTP CAMERAS | MEDIUM | Researching 50/50 grant | IDLE
VILLAGE WIFI | MEDIUM / LOW | Met with the GTB regarding WIFI for our residents 7-22-19. A proposal is forthcoming. | INITIATED
PAINT BATHROOMS @ DUESTER PARK | MEDIUM / LOW | Exterior of building needs attention UPDATE- Requested to be initiated again on 7-17-19 Update; postponed due to seiche actions. | COMPLETE
BAHLE PARK TREE EVALUATION | MEDIUM / LOW | General Committee at their 9-3-19 meeting has indicated this is a priority. Staff evaluated trees per committee. UPDATE - Duester Park tree cutting quote received. Dangerous tree quote received 10-7-19 dated same. Project completed per estimates. | COMPLETE
DEUSTER PARK SOCCER | MEDIUM / LOW | Met with Suttons Bay Schools Coach and Leelanau Soccer Club representative regarding the continued use of Deuster fields and upgraded bathrooms. UPDATE: Verbal agreement regarding a partnership with Leelanau Soccer Club & Suttons Bay School for use of park bathrooms. | COMPLETE
DEUSTER PARK DOORS | MEDIUM / LOW | Bathroom doors are damaged - Door knobs do not comply with ADA requirements. UPDATE: 11-25-19 Door initiative taken over- being re-measured 11-25-19. UPDATE 11-27-19 Doors being ordered in January due to budget. | COMPLETE
PORT SUTTONS MAINTENANCE AGREEMENT | MEDIUM / LOW | Still learning about this subject | IDLE
GIS- SHP FILES FROM LEELANAU COUNTY | MEDIUM / LOW | Need this information to build the GIS - UPDATE- F&V obtaining SHP files for Village and Township. Study of lakefront districts to be studied early 2020. | COMPLETE
LAKEFRONT LOT SIZE STUDY | MEDIUM / LOW | COMPARE LOT SIZES / VARIANCE REQUESTS / CONSTRUCTION DATES TO DETERMINE IF ANOTHER DISTRICT OR DIMENSIONAL VARIATIONS ARE NEEDED. UPDATE: 9-19-19 - UPDATE: Study of lakefront district will occur in January of 2020. | IN PROGRESS
ZONING ORDINANCE | MEDIUM / LOW | The new Ordinance fails to implement "form" as intended. Standards are missing, definitions don’t match terminology etc. Previously a HIGH priority downgraded until training for PC occurs. | INITIATIVE RETRACTED
BAYVIEW ZONING / Development incentives | LOW | This initiative has been retracted until proper training for PC to understand the modifications proposed. | INITIATIVE RETRACTED
MARINA ORDINANCE | LOW | The Marina Ordinance is dated and should be updated to prepare it for granting opportunities. EAST side. We should also look to replace the bathrooms as a part of the grant application. | IDLE
VILLAGE HALL COPIER | LOW | Discussion had with current vendor- Looking elsewhere. UPDATE - Meeting Scheduled for 7-16-19 UPDATE: Moving forward with new copier contract signed 7-23-19 | COMPLETE
STREET CAMERAS | LOW | Researching 50/50 grant | IDLE
FERRY INITIATIVE | LOW | Discussions ongoing with Elk Rapids. An evaluation of the marinas indicate VSB can (physically) accommodate a ferry however Elk Rapids provides larger challenges. UPDATE: DDA to discuss Ferry on 10-9-19. UPDATE: Ferry Presentation before VC- 11-18-19. | IN COMMITTEE
SUTTONS PARK CAMERAS | LOW | Researching 50/50 grant- Grant Submitted 10-3-19 | COMPLETE - APPLIED
POLICY VILLAGE HALL RENTAL | LOW | A sub-committee to discuss this issue will be needed to determine a need or direction. UPDATE: Committee members were looking into this. UPDATE: Study Completed going before General Committee on 11-5-19 | COMPLETE
POLICY - MEMORIALS | LOW | A sub-committee to discuss this issue will be needed to determine a need or direction. UPDATE: :Committee members were looking into this. | IN COMMITTEE
MARINA WETLAND EVALUATION | LOW | Discussions to review and possibly eradicate invasive species. Currently Speaking with ISN. UPDATE: A review has been completed and information provided. | COMPLETE
HARBOR MASTER CONTRACT | LOW | SIGNED 2019 UNTIL JANUARY 2020/ WILL INCREASE IN PRIORITY AS THE YEAR PROGRESSES - UPDATE: Request for increase in pay received 10-2-19. UPDATE: Discussions ongoing. Recommendation to the Personnel Committee for 11-6-19 UPDATE: Contract Signed. | COMPLETE
WWTP OPERATIONS CONTRACT | LOW | SIGNED 2019 UNTIL DECEMBER 2020/ WILL INCREASE IN PRIORITY / EVALUATING STAGE FOR 2 YEAR EXTENSION. UPDATE: 10-2-19 meeting held- informed them that no contract discussion was needed at this time. | IDLE
SHERIFF CONTRACT | LOW | CONTRACT DISCUSSIONS HAVE TAKEN PLACE - UPDATE: -S. Morgan provided the rough draft with the 1-year extension as accepted by LC. | COMPLETE
RAINGARDEN PARTNERSHIP | LOW | Children's House initiative - UPDATE: Maintenance of raingardens scheduled - UPDATE: Maintenance of raingardens complete.. Great initiative! | COMPLETE
TREE PLANTING INITIATIVE | LOW | Sicily Sanford - Citizen Volunteers requested permission to plant trees in partnership with CRA. UPDATE: Initiative scheduled/completed. 400+- trees planted. | COMPLETE
PARKS & REC BYLAWS | LOW | DRAFT CREATED ON HOLD UNTIL ORDINANCE IS ADOPTED.- UPDATE - PC Subcommittee was requested therefore initiative is tabled. | INITIATIVE RETRACTED
SPLIT RAIL FENCE REMOVAL | LOW | Removal of split rail fence on north and south sides of Village Hall. | COMPLETE
CONGRATS! YOU MADE IT THROUGH MY WORK PLAN AND DIDN’T FALL ASLEEP!

## 2020
PROJECT | PRIORITY LEVEL | DESCRIPTION | STATUS
PARKS & RECREATION PLAN | HIGH | Suttons Park & waterwheel plan has been designed and accepted by PC. UPDATE; 9-14-20 Review of former Goals And objectives are progressing. | IN PROGRESS
MASTER PLAN | HIGH | Update the Master Plan / Separate from Joint Master Plan | IDLE
2020 VEHICLE PURCHASE | HIGH | UPDATE: 7-29-20 Vehicle delivered! | COMPLETE
2020 VEHICLE LOGOS | HIGH | Vehicle logos have been proofed and ordered for 4 of the DPW vehicles and one for the Gator. Installation anticipated in the near future. | COMPLETE
VACATION HOME RENTAL ORDINANCE | HIGH | Poorly Drafted - Requires to be re-written. UPDATE: The Michigan Supreme Court has agreed to hear arguments regarding the commercial vs residential use. To date: The appellate courts have continued to view STR's as a commercial use that is prohibited in residential districts. | IDLE
PURCHASE OF FOGGING MACHINE | HIGH | UPDATE: 7-28-20 -Purchased and in use. This will be used to sterilize the DPW facility as well as the Administrative offices. | COMPLETE
BEACH GROOMING | HIGH | UPDATE: 7-28-20 Beach grooming will take place in the next two weeks to avoid a stagnant water concerns. | COMPLETE
S.SHORE DRIVE EMERGENCY | HIGH | 12-12-19 Meeting on site with LCRC on erosion issues and emergency armoring of S.Shore Drive. Agreement signed 1-7-20 - Work has commenced. | COMPLETE
LITIGATION | HIGH | In process Detail not available. | IN PROGRESS
HIGH WATER / EROSION Resolution to Gov. | HIGH | Jack O'Malley contacted my office regarding resolution (6-10-20) mailed on behalf of numerous Leelanau County municipalities. No reply from the State. | COMPLETE
HIGH WATER / EROSION COLLABORATION | HIGH | UPDATE- February - Scheduled a meeting and met with surrounding municipalities, Counties and emergency manager. | COMPLETE
NEW LAND DIVISION ORDINANCE | HIGH | Pre-draft Completed on 1-8-20. Review forthcoming. New Applications, approval documents and checklist for applicants to ensure completed applications and procedural understanding. UPDATE: February- Moved to VC for consideration. UPDATE: Canceled due to COVID-19 - UPDATE: 7-30-20 We will be moving forward with the LDA Draft and reschedule. | COMPLETE
STREET CLEANER | HIGH | Pricing equipment to street clean due to high cost of $225/hr. @ 25 hours, Does not include M-22 UPDATE: Modified to include M-22 due to lack of urgency associated with TAP contractor. Pushed back to July 6th due to work load. | COMPLETE
DRAFT NEW ZBA BYLAWS | HIGH | Pre-draft Completed For ZBA Discussion. Provided at the January meeting. | COMPLETE
FIREWORKS ORDINANCE Amendment | HIGH | Ordinance is dated and does not conform to State law. Updates required. UPDATE: Ordinance is now complete due to being pushed back due to COVID-19. Will be provided to committee for consideration in July. UPDATE: 7-9-20 Committee elevated this to VC. | COMPLETE
STREET EVALUATION SOUTH SHORE | HIGH | UPDATE: 7-9-20 Contract signed with Elmer's to patch the hump once fixed. KAL will be hired to replace the culvert. Summer project. UPDATE 10-02-20 - Work to begin in October by Elmer's. | IN PROGRESS
BROADWAY STREET | HIGH | UPDATE: 8-25-20 - The agreement was finalized. Topo provided to engineer. UPDATE: 8-26-20 Met with engineer on site with topo to discuss a plan. Proposal forthcoming. UPDATE: 9-14-20 Plan received and will be displayed. 10-02-20. Contract signed project a go for Phase #1. | IN PROGRESS
CROSS CONNECTION ORDINANCE | HIGH | MDEQ REQUIREMENT | IDLE
ZONING MAP | HIGH | Adopted Zoning Map is incorrect and requires an amendment. Update: Planning Commission Scheduled a Public Hearing (3-11-20) UPDATE: Village council adopted change in June. New Map has been created. | COMPLETE
CONSUMERS ENERGY GRANT | HIGH | This is a high level priority due to time constraints. Application has been submitted 2-26-20 to create a Hydro Charge Park. H20-power for EV charging stations. Not Selected. | COMPLETE
MARINA BOAT LAUNCH CLOSURE | HIGH | DUE TO HIGH WATER AND SAFETY CONCERNS ASSOCIATED WITH THE MARINA LAUNCH WE ARE EVALUATING IT FOR CLOSURE. UPDATE See Report VSB-2020-06 Update: VC Agenda for 2-17-20 - VSB 2020-13- Temporarily CLOSED | COMPLETE
MARINA PARK CLOSURE TO FESTIVALS | HIGH | Committee to discuss the closure of Marina Park to festivals / Mass Gatherings | COMPLETE
EMPLOYEE RETIREMENT LEGAL ISSUE | HIGH | An Attorney has been retained to address issues regarding the Village retirement accounts. UPDATE: February- Conference calls with Attorneys and KDP. Direction for resolve provided. Ongoing issue, however, we are on the right track to resolve issue without litigation. 401 vs 403 | COMPLETE
TAP PROJECT | HIGH | UPDATE: 7.30.20. Paving sub-contractors "fix" needs to be fixed again as do some concrete issues. A second "final" walkthrough is forthcoming. | COMPLETE
STREET EVALUATION - ELM STREET | HIGH | UPDATE: 7.30.20 collaboration has begun. UPDATE 9-14-20: Met last week with Elmer's on site with DPW Director. UPDATE: 10-01-02 - Proposal to go before VC for consideration and budget consideration (2021 summer project). | IN PROGRESS
NORTH PARK BATHROOM UPGRADE | HIGH | Replace faucets with "timed" faucets and replace counters. Both faucets broken and counters rotted. UPDATE: Faucets ordered. UPDATE: 7-30-20 Timed faucets have been installed, counter tops will be an offseason project. | COMPLETE
INLAND SEAS LEASE AGREEMENT | HIGH | 8-24-20 - Draft lease agreement complete and being reviewed by Harbor Master. UPDATE: 9-1-20 Draft Lease agreement emailed to ISEA for review. UPDATE: 10-02-20 response received will evaluate. | IN PROGRESS
LAKEFRONT LOT SIZE STUDY | HIGH | UPDATE: 7-30-20 - To be presented at the August PC meeting. A draft has been provided to the PC for evaluation, comments and questions. August: Walking tour of properties took place. UPDATE: Residents concerned with possible changes. Door to door survey to be performed by PC members. | IN PROGRESS
STREET TREES | HIGH | UPDATE: 6-18-20 - Various trees identified for removal. Next step: contact / contract with tree removal company. Various street trees have been identified and appear to have been ignored for years. Tree company has been contacted, UPDATE: Contract signed to remove / trim 9 trees. Trees removed. | COMPLETE
WATER RESERVOIR EXPANSION | MEDIUM / HIGH | Per MDEQ additional water storage is REQUIRED - this item was recommended by the MDEQ in 2018. UPDATE: F&V reviewing financials and eligibility for granting opportunities. UPDATE: Met with F&V to discuss expansion initiative. 40 year loan @ 2.5%(ish) on $2.5 million loan would cover line upgrade northern loop, reservoir, and 2 new wells. Next steps forthcoming. See rate note below. | IN PROGRESS
WATER RATES | MEDIUM / HIGH | EVALUATION OF WATER RATES UPDATE: F&V UPDATE: Reviewing UPDATE: Met with F&V to discuss expansion initiative. RATES would see less than $4.00 / month increase for reservoir expansion etc. listed above to cover that project for life of loan. | IN PROGRESS
WATER WELL PROTECTION GRANT | MEDIUM / HIGH | Grant secured by EGLE. Step #2 is to create a new program. | COMPLETE
WATER WELL PROTECTION PROGRAM | MEDIUM / HIGH | UPDATE: 7-30-20 Grant submitted. UPDATE: 10-01-20 - New program completed and submitted. | COMPLETE
ZONING FENCE AMENDMENT | MEDIUM / HIGH | Section 2-21 of the VSB zoning ordinance requires clarification and clarity. | INITIATED
MARINA BRIDGE | MEDIUM / HIGH | UPDATE: Bridge removed | COMPLETE
ARCHITECT - ADA COMPLIANT DECK | MEDIUM / HIGH | Funding retracted by committee. All involved have been notified that project is a no go. No further action to be taken without full VC direction by motion. | INITIATIVE RETRACTED
VILLAGE WATER ORDINANCE | MEDIUM / HIGH | This item has been recommended by the MDEQ in 2018 - Ordinance dated needs attention - F&V to review and provide direction. Contract needed | INITIATED
GPS SERVICES | MEDIUM | There have been several discussion with the vendor working towards a free 30-60 day unit and service. - Wil meet in fall to continue discussions. - UPDATE: Trial period accepted by vendor. BUDGET 2021 | IDLE
MSU EXTENSION PARTNERSHIP | MEDIUM | UPDATE: Email exchange on 7-28-20 - The Village was asked to identify areas that could benefit from this partnership to begin discussions. UPDATE: 8-2020 MSUE representative is evaluating the sites identified. UPDATE: 10-01-20 - Project agreements submitted - partnership initiated. | COMPLETE
JEFFERSON STREET PEDESTRIAN COURT | MEDIUM | Temporary Closure for pedestrian use? UPDATE: NEW location to be proposed (trailer parking) following TAP project? | INITIATIVE RETRACTED
PEDESTRIAN SQUARE INITIATIVE | MEDIUM | Boat trailer parking area to be temporarily used as a seating and viewing area. This initiative will replace the Jefferson Street Pedestrian Court initiative. UPDATE: 3-3-20 Meeting with DPW Staff to brainstorm ideas. UPDATE: May 2020: seating area created in trailer parking area &Grove road end. | COMPLETE
PEDESTRIAN SEATING AREAS DOWNTOWN | MEDIUM | $8,000 Allocated to downtown furniture and bike racks for pedestrian comfort. This will follow an evaluation of the finalized TAP project to determine locations. | COMPLETE
WATERWHEEL PARK | MEDIUM | . UPDATE: RFP and EGLE review needed to determine what we can do to the stream / dam. UPDATE 6-25-20: RCA Contacted regarding consultation on Waterwheel. UPDATE 7-30-20 (See Parks & Recreation Plan update) | IN PROGRESS
VILLAGE STREET -WEIGHT LIMITS | MEDIUM | Vehicles with excess weight damaging Village Streets. Weight limits on numerous roadways including Elm to circumvent unnecessary weight and short cuts by semi-trucks. UPDATE: 9/19 Meeting scheduled with LCRC. | IDLE
PAVING PROJECT - PARK WALKWAY | MEDIUM | South Shore/Suttons Park - create pedestrian circulation, reclaim park from parking area. Angle 20-23 ft. UPDATE: Elmer's proposal recommended to Village Council. UPDATE: Proposal signed - awaiting timing of project. | INITIATED
2% GRANT PARTNERSHIP | MEDIUM | A successful 2% grant application. Looking forward to this partnership with the GTB. | COMPLETE
CHARTER CABLE EXTENSION DPW | MEDIUM | Discussions with Charter on expanding service to the DPW to properly service the WWTP, offices, etc. UPDATE: Charter measured distance 9-19. waiting on cost and timeframe. | COMPLETE
DPW/WWTP CAMERAS | MEDIUM | Researching 50/50 grant | IDLE
US BR 35 RE-ROUTE | MEDIUM | Application complete - See VSB-2020-05 UPDATE: VC consideration 2-17-20 UPDATE: MDOT has reviewed the request and is recommending the change to AASHTO. Change adopted. | COMPLETE
RAINGARDENS | MEDIUM | UPDATE; 6-18-20 - Met with Sarah U'Ren on updating raingardens. Direction to improve RG's next week. UPDATE: 7-14-20 Two downtown raingardens updated. Remaining downtown raingardens to be improved in Fall. | COMPLETE
INTERGOVERNMENTAL AGREEMENT SEWER & WATER | MEDIUM | Intergovernmental agreement for water & sewer services outside of Village limits is in need of review and re-drafting. | INITIATED
VILLAGE WIFI | MEDIUM / LOW | Met with the GTB regarding WIFI for our residents 7-22-19. A proposal is forthcoming. UPDATE: 10-01-20 - Discussions with GTB representatives have been re-initiated. | INITIATED
PORT SUTTONS MAINTENANCE AGREEMENT | MEDIUM / LOW | Still learning about this subject | IDLE
GIS- SHP FILES FROM LEELANAU COUNTY | MEDIUM / LOW | Need this information to build the GIS - UPDATE- F&V obtaining SHP files for Village and Township. Study of lakefront districts to be studied early 2020. | COMPLETE
VIKING CRUISE LINES | MEDIUM / LOW | Discussion at the sub-committee meeting recommended further discussion. UPDATE; 7-30-20- A meeting is anticipated to discuss Vikings intent and desires. | INITIATED
ZONING ORDINANCE | MEDIUM / LOW | The new Ordinance fails to implement "form" as intended. Standards are missing, definitions don’t match terminology etc. Previously a HIGH priority downgraded until training for PC occurs. UPDATE: 10-02-20- Various changes moving forward. | INITIATED
VISITOR BATHROOMS | MEDIUM / LOW | New bathrooms for year round use? Committee did not feel it was a Village goal at this time. | COMPLETE
DOWNTOWN BANNER POLICY | MEDIUM / LOW | Downtown banners require compliance with MDOT regulations. Village policy may be necessary to ensure oversight. | INITIATED
BAYVIEW ZONING / Development incentives | LOW | This initiative has been retracted until proper training for PC to understand the modifications proposed. UPDATE: August Letter sent to all PUD owners .UPDATE 10-01-20 - 3 of 4 property owners have shown interest. All owners needed for Village initiative. Project retracted until further cooperation is obtained. | COMPLETE
MARINA MASTER PLAN | LOW | The Marina Ordinance is dated and should be updated to prepare it for granting opportunities. EAST side. We should also look to replace the bathrooms as a part of the grant application. | INITIATED
SUTTONS PARK CAMERAS | LOW | GRANT AWARDED - UPDATE: 6-24-20 Met onsite with contractor to determine an implementation strategy and timeframe. UPDATE: 7-29-20 - New pole installed, cable installed, now awaiting camera installation. | COMPLETE
M-22 DOWNTOWN STREET CAMERAS | LOW | 50/50 grant for Cameras to be granted. Grant Administrator required a decision to be made on 1 of 2 grants. We will proceed with the Suttons Park grant. UPDATE: 7-29-20 - Discussion on subject at COW to strategize and/or budget for 2021. | INITIATED
BAHLE HUT PARK TREE HARVESTING | LOW | Tree cutting or harvesting to be discussed to widen the sledding hill. | IDLE
FERRY INITIATIVE | LOW | Initiative postponed. | POSTPONED
ICE RINK PARK | LOW | Discussions on park partnership have not materialized. Village has questioned if the Township would like to relinquish the park to Village. UPDATE: 7-30-20 - -This subject remains idled however the parcel would be ideal for a dog park in the spring/summer/fall months and ice rink in winter. | IDLE
POLICY - MEMORIALS | LOW | A sub-committee to discuss this issue will be needed to determine a need or direction. UPDATE: :Committee members were looking into this. | IDLE
LAW ENFORCEMENT CONTRACT | LOW | Contract expires at the end of 2020 - Discussions needed for extension UPDATE 6- 11-20- Morgan dropped off a preliminary cost figure for 2021. UPDATE: 7-30-20 - Agreement reached on 2021 contract, awaiting finalized copy. UPDATE: 8-24-20 Contract signed and sent to the County for consideration. UPDATE: 10-01-20 - Awaiting a copy of approved contract. | COMPLETE
WWTP OPERATIONS CONTRACT | LOW | 8-25-20 Contract extension of 1 -year has been signed by both parties for 2021. | COMPLETE

## 2021
PROJECT | PRIORITY LEVEL | DESCRIPTION | STATUS
PARKS & RECREATION PLAN | HIGH | Maps complete - Contrary to the public comments at PC and VC meetings, 2020 Census data is still NOT available. Once received a timeline can be placed on the completion of the draft. | IN PROGRESS
MASTER PLAN | HIGH | Update the Master Plan - Contract secured - The process will begin in 2022. | COMPLETE
ELM STREET PAVING | HIGH | Project began August 25th and completed on August 27th. | COMPLETE
ELM STREET GRANT | HIGH | Application did not receive funding. | COMPLETE
ELM STREET CULVERTS | HIGH | Discussions with State, regional and local offices… These culverts do not qualify for the grant proposed by the Twp committee. | COMPLETE
ELM STREET BRIDGE LAWSUIT | HIGH | The Village was successful in securing the full amount for repair ($39,441) from the defendants insurance company, less attorney fees. (the village was offered $3,000 prior to lawsuit). | COMPLETE
INLAND SEAS LEASE AGREEMENT | HIGH | 10- Year Contract Signed - Provisions to be reviewed every 2 years with yearly Marina/Inland Seas staff meetings to improve communication. | COMPLETE
BROADWAY ROAD RAINGARDENS | HIGH | Searching for original calcs to avoid having to pay engineer. Two Broadway Road raingardens located at Lincoln and Broadway are likely to be eliminated in the Spring. | COMPLETE
FEMA - FIRM MAP | HIGH | Map open houses held January 5th & 7th by FEMA | COMPLETE
WATER RESERVOIR INITIATIVE | HIGH | Discussions on financing multi-phase projects being investigated. | IN PROGRESS
WELLHEAD PROTECTION PROGRAM | HIGH | PLAN RECEIVED | COMPLETE
SOURCE WATER PROTECTION GRANT | HIGH | A grant was received (Nov. 1st) to continue study. Meeting held 11-12-21. | COMPLETE
RECYCLING COMPLAINTS | HIGH | A meeting with the County officials that proved unproductive following a fact check. | COMPLETE
VACATION HOME RENTAL ORDINANCE | HIGH | The State - House - has passed the Bill to eliminate most local control. No known Senate decision. | COMPLETE
SANITARY SEWER FIX | HIGH | DPW Identified a broken line that requires repair. See David Millers staff report. Hired a company to video the line for comparison to the SAW video. | COMPLETE
LITIGATION | HIGH | All counts of Bob Joyce vs Village of Suttons Bay have been dismissed by the 13th Circuit Court. Joyce did not appeal. Case closed. | COMPLETE
ZONING ORDINANCE REVIEW | HIGH | A re-write of the zoning ordinance is needed for successful development and redevelopment within our commercial core. | INITIATIVE RETRACTED
PLANNING CONSULTANT | HIGH | Contract Signed. | COMPLETE
BLIGHT ORDINANCE | HIGH | The new Blight Ordinance will be introduced in early 2022. | COMPLETE
REC VEHICLE PARKING ORDINANCE | HIGH | Unattached trailer parking on Village street prohibition. DRAFT 1 Complete. This initiative is being retracted due to the difficulty of enforcing this Ordinance without a Village police department. | COMPLETE
MARINA ORDINANCE AMENDMENT | HIGH | The Marina Ordinance is being amended to address a few seasonal issues. Draft to be proposed at April Committee meeting. Adopted. | COMPLETE
TAP PROJECT | HIGH | The TAP project has been finalized…. | COMPLETE
WASTEWATER TREATMENT PLANT CAMERA GRANT | HIGH | Received Grant from Risk Reduction Grant Program. | COMPLETE
S. SHORE "HUMP" FIX | HIGH | Repair of the nemesis S. Shore "hump". | COMPLETE
S. SHORE DRIVE EVALUATION | HIGH | Contract approved by VC for engineer to review and recommend potential modifications to mitigate overflow of water from wetlands. | IN PROGRESS
WEST ROAD TREE REMOVAL | HIGH | Despite the neighbor requesting a protest, owners supported the removal of dead and dangerous trees. Trees removed and stumped. | COMPLETE
WEST ROAD SIDEWALK | HIGH | This project was anticipated to start in May however, staffing and availability of workers have affected all businesses. Project now slated to begin in October. November. December. | IN PROGRESS
MARINA / BARKENTINE WALKWAY | HIGH | Necessary improvements to the walkway connecting Marina patrons with the restrooms. This walkway was deemed a hazard due to the washouts and brick movement. Projected completed. | COMPLETE
WEDGE POCKET PARK | HIGH | Wedge Park is now open and generating excitement among visitors of the park and residents alike. The grass is growing well, old stumps have been ground down, the fence has been repaired, and the old bench has been removed to emphasize the creek. “Jack’s” water bottle filler is now installed. | COMPLETE
SUTTON PARK PLATFORM COLLAPSE | HIGH | Project Completed and restored with grass and riprap. | COMPLETE
VILLAGE AUDIT | HIGH | The annual audit is complete and has been reviewed. Thank you Lorrie for all your hard work. | COMPLETE
SUTTON PARK FENCE | HIGH | We will be installing a fence on the property line between Sutton Park and Suttons Bay Cottages due to the continual violations by renters parking on the park lawn. | IN PROGRESS
NORTH PARK CAMERA GRANT | HIGH | 50/50 grant submitted for wireless cameras. Grant Received 8-2-21 for $2,500. Purchase and Installation is next. | COMPLETE
NORTH PARK CAMERA PURCHASE / INSTALLATION | HIGH | All cameras are installed. | COMPLETE
WASTEWATER TREATMENT PLANT CAMERA PURCHASE / INSTALLATION | MEDIUM | Installed 4-27-21. $2,500 grant reimbursement received. | COMPLETE
WASTEWATER TREATMENT PLANT - FENCING & GATES | MEDIUM | We continue moving forward with securing the DPW and wastewater treatment plant. The installation of fencing and gates to limit entrance onto the property will follow surveyors findings. | IN PROGRESS
INTERGOVERNMENTAL AGREEMENT SEWER & WATER | MEDIUM | The Utilities Committee -wastewater treatment plant’s capacity with reserved capacity too high to offer outside Village services at this time. | COMPLETE
MARINA WALKWAY REMOVAL | MEDIUM | Dilapidated and hazardous wood walkway removed adjacent to Millside. | COMPLETE
M-22 SIDEWALKS | MEDIUM | Extension of sidewalk located on the east side of M-22 to access Suttons Park and Hansen's. | INITIATIVE POSTPONED
PEDESTRIAN LIGHT (MDOT) | MEDIUM | Requires partnership with MDOT. Positive discussions have taken place. Sidewalk extension to Suttons Park is a prerequisite...More to come…. | INITIATIVE POSTPONED
MASTER PLAN SURVEY | MEDIUM | The PC continues to work on this initiative. | IN PROGRESS
DOWNTOWN BUSINESS SURVEY | MEDIUM | This will likely be drafted and discussed at the VC / DDA level. | IDLE
DOWNTOWN BANNERS | MEDIUM | Banners for our downtown light poles have been installed. | COMPLETE
PLOW TRUCK | MEDIUM | Following several months of research and discussions we are now pricing a new plow truck. | IN PROGRESS
PLOW TRUCK WING | MEDIUM | Research continues.. | IDLE
MARINA BRIDGE REPLACEMENT | MEDIUM | Soil borings to determine if we can construct the bridge with pylons is being priced. Soil borings complete. Waiting on engineer review and recommendation as a part of the contract. | IN PROGRESS
MSUE GARDNER PROGRAM - PARTNERSHIP INITIATIVE | MEDIUM | MSUE Master Gardener program - Projects identified - Implementation postponed due to C-19. | INITIATIVE POSTPONED
WALL MOUNTED WATER BOTTLE FILERS | MEDIUM | Researching 4 water fountains with bottle filler. Cost has increased nearly 75% since 2020 looking at best options may have to change strategy. Cost anticipated to drop once supply increases-will try in 2022. | INITIATIVE POSTPONED
IDENTIFY ARTISTS | MEDIUM | Explore artistic talents of our residents both young and experienced and identify the community benefit such as murals etc. | IDLE
NORTH PARK BARRIER STRUCTURES | MEDIUM | A local man struck a height restriction barrier at N. Park with his sailboat mast. Despite leaving the scene, we were able to identify him and send the information to officer Donahue. He is being charged the cost to repair the structure. | COMPLETE
SUTTONS PARK WALKWAY | MEDIUM | We are seeking an estimate for a concrete walking path through the park for installation. This summer 2021 project is now planned for Spring 2022. The labor shortage has proven difficult for local businesses. We will shift to TC based businesses in 2022. | IN PROGRESS
ELM STREET WEIGHT RATING | MEDIUM / LOW | Investigation on the procedure to evaluate and adjust the weight rating on Elm Street has been initiated. | IN PROGRESS
DOWNTOWN STREET LIGHTS | MEDIUM / LOW | Research forthcoming | IDLE
VILLAGE WIFI | MEDIUM / LOW | Tribal representatives provided Staff with an estimate for this service. The six -figure estimate is unfortunately too high to consider. This initiative is being retracted due to cost. | COMPLETE
ELMER'S STREET EVALUATION | MEDIUM / LOW | A meeting with Elmer's representatives to evaluate 3 roadways took place on 6 7-21. These meetings are intended to understand a cost to fix our most challenging roadways so we can budget appropriately. | COMPLETE
VIKING CRUISE LINES | MEDIUM / LOW | Discussions have reopened regarding this initiative. Some negotiations are ongoing to determine benefits vs cost. | IN PROGRESS
STORM DRAIN RESTITUTION | MEDIUM / LOW | We are working to secure restitution for damage caused to a storm cover and safety post. (P vs Elliott Boyadjian) PAID IN FULL. | COMPLETE
SALT STORAGE BARN | MEDIUM / LOW | Determining need. Not a priority at this time. | COMPLETE
ADOPT A BASIN | MEDIUM / LOW | Discussion with City of Traverse City on this initiative is forthcoming | IDLE
ADOPT A RAINGARDEN | MEDIUM / LOW | Raingarden plants are proving difficult to find. More to come…. | IDLE
DOWNTOWN CAMERAS | MEDIUM / LOW | Cameras will be located at all crosswalks. Focus switched to North Park due to vandalism. | INITIATIVE POSTPONED
SAIL SHADE PROJECT | MEDIUM / LOW | A sail has been donated to provide shade for the pop-up park. Thank you Hakuna Matada! | COMPLETE
SAIL SHADE INSTALLATION | MEDIUM / LOW | The DPW has been preparing poles etc. for the installation of the sail. | INITIATED
DDA - OPT OUT | MEDIUM / LOW | County and Township maintain they would consider a case by case proposal for a DDA capture but still not all in. This stance has not changed. | COMPLETE
LAND DIVISION ORDINANCE | MEDIUM / LOW | Public Hearing 3-15-21 - Adopted by VC | COMPLETE
SUTTONS PARK - PARKING LOT RECLAMATION | MEDIUM / LOW | The current parking lot is to be reclaimed to eliminate the traffic safety issue caused by a lack of curb cut. Parking will be relocated to be parallel with M-22. A curb cut will be added to provide safe ingress and egress of vehicles. | INITIATIVE RETRACTED
DOWNTOWN BANNER POLICY | MEDIUM / LOW | Discussion to only allow Village banners supported by committee. | COMPLETE
MEETING ROOM ACOUSTICS | MEDIUM / LOW | Ongoing search for local company to evaluate and provide a solution. No luck with finding a local company. | IDLE
LEAF / GRASS REMOVAL CHANGES | MEDIUM / LOW | Proposal to streamline leaf and grass removal to a more structured practice. | COMPLETE
VILLAGE CLEAN UP PRACTICE CHANGE | MEDIUM / LOW | By moving the Village clean-up day to the Fall, it would provide our residents with the ability to utilize both the Township event and Village event. Committee has recommended that we change this event to the Fall for 2021. | COMPLETE
PARK SIGNS | LOW | Awaiting cost on signs. | COMPLETE
STREET TREES | LOW | Street tree replacement is an ongoing endeavor due to the age of our street trees. | COMPLETE
STREET TREE POLICY | LOW | The committee has agreed that a new street tree policy should be drafted with the focus being the village. | IDLE
MAP AMENDMENT | LOW | A zoning map amendment to fix the inadvertent rezoning of properties (that occurred when the new zoning map was adopted) has been recommended for approval to the Village Council. | COMPLETE
DPW FUEL STATION | LOW | No short term intent we are simply researching if having our own fuel station would be feasible. | IDLE
ZONING FENCE AMENDMENT | LOW | A text amendment to eliminate the fence setback has been initiated and been recommended to the Village Council for consideration. | COMPLETE
MARINA MASTER PLAN | LOW | The Marina Master Plan review continues. Upgrade necessary. | IN PROGRESS
TOWNSHIP CULVERT INITIATIVE | LOW | Letter to Township Board requesting intent and clarification has been sent but did not receive a response from the Board. Retracted | COMPLETE
PART TIME DPW POSITION | LOW | Determined to be a need. | COMPLETE
NEW VOLLEYBALL COURTS - MARINA PARK | LOW | Volleyball Nets Installed at Marina Park. | COMPLETE
LAW ENFORCEMENT CONTRACT | LOW | 1-year extension finalized. | COMPLETE
WWTP OPERATIONS CONTRACT | LOW | Negotiating. The Village has proposed another 1-year extension. | COMPLETE
VEHICLE LOGO | LOW | All DPW Vehicles are now outfitted with new Village Logo. | COMPLETE
GRAVEL MUNICIPAL LOT | LOW | Municipal parking lot located on Cedar/1st street needs maintenance gravel. | COMPLETE
FLAG POLE | LOW | Pricing flag pole for the Village Hall | INITIATED

## 2022
PROJECT | PRIORITY LEVEL | DESCRIPTION | STATUS
WATER RESERVOIR STATE LOAN INITIATIVE | HIGH | 3-15-22 - Preliminary point system indicates that we are unlikely to receive a loan despite being the only community in northern Michigan to apply and having more points than other communities. 6-15-22- Initiative retracted. | COMPLETE
WATER RESERVOIR USDA LOAN INITIATIVE | HIGH | We will retract interest and shift focus. | COMPLETE
PARKS & RECREATION PLAN | HIGH | The Village Council approved the Plan at their November meeting. 7-0 | COMPLETE
MASTER PLAN | HIGH | The Master Plan process continues. | IN PROGRESS
WATERWHEEL SINKHOLE | HIGH | A liner to temporarily re-route the creek has been purchased. I am working with the engineer, State, stream restoration experts etc. to find a solution to the crumbling waterwheel structure, applying for permits, etc. The structure was further compromised and required an emergency removal on 10-26-22. Stream was re-routed on 10-25-22. | IN PROGRESS
WATERWHEEL RESTORATION | HIGH | A cost estimate of $300,000 was provided by our consulting engineer and provided to the VC at their 10-17-22 meeting. | IN PROGRESS
WATERWHEEL REMOVAL | HIGH | A contract was signed with an alternate engineer to create a plan and determine a cost estimate to move forward without the waterwheel. Contract signed 10-17-22. A kickoff meeting was held on 10-26-22 The structure was removed on 10-26-22. | COMPLETE
BLIGHT ORDINANCE | HIGH | The Blight Ordinance was discussed at committee and final enforcement tweaks are being made. Staff will recommend not adopting the Ordinance due to a lack of need and a lack of understanding on what would be considered blighted. | COMPLETE
WEST ROAD SIDEWALK | HIGH | Working to coordinate our workers to remove sidewalk and have forms and concrete completed by contractor. Form installation being completed 8-1-22. Concrete expected to be completed on 8-4-22. Weather permitting. | COMPLETE
MARINA ORDINANCE UPDATE | HIGH | A complete re-write is being considered to bring the Ordinance to a more modern standard. | IN PROGRESS
DDA MEMBER RESEARCH | HIGH | Active DDA members had requested Staff to review the possibility of decreasing the amount of members appointed to the DDA Board. This request was made following a lack of members participating in meetings resulting in a lack of quorum more often than not. The answer is no. We are at the State minimum of 8 members unless we make the PC the DDA also, which is an option. | COMPLETE
WEST / LINCOLN PAVING PROJECT | HIGH | West and Lincoln Street mill and fill repaving project complete. | COMPLETE
ROWING EVENT | HIGH | Meeting with event organizers to address geographic, social and physical concerns associated with our location prior to application submittal. Meeting with event organizers went well and we are progressing. Organizers had an event conflict and retracted their request. | COMPLETE
ELM STREET 3-WAY STOP PROJECT | HIGH | Majority vote to move forward with the proposal. Contract signed & sent on 6-21-22. Study received and being reviewed. | COMPLETE
WASTEWATER TREATMENT PLANT - FENCING & GATES | HIGH | We continue moving forward with securing the DPW and wastewater treatment plant. The installation of fencing and gates to limit entrance onto the property will follow surveyors findings. The property line is located in a manner that we will need to adjust the North entrance. Stay tuned... | IN PROGRESS
SHORT TERM ORDINANCE REVIEW AND UPDATE | HIGH | Moratorium passed 90-days as of 6-20-22. Initiative extended and sent to a consultant. Consultant findings discussed in October. Tier 1 amendments approved at 11-21-22 mtg. | COMPLETE
M-22 RESURFACING PROJECT | HIGH | The resurfacing project was completed in 1-week. | COMPLETE
PAVILION ACQUISITION | HIGH | Cost estimate has been provided following meetings with builder, crane operator and concrete businesses. Proposal recommended by committee to VC for consideration. VC voted down 4-3 to spend $17,000 for a park pavilion. | COMPLETE
VILLAGE ENTRY SIGN | HIGH | The design has been finalized. Working with MDOT to move the sign closer to the roadway as a part of the upgrade. Relocation is not justifiable. | COMPLETE
PARK IDENTIFICATION SIGNS | HIGH | We are moving forward with our phase #1 of identifying our parks. Two signs have been ordered into production. | COMPLETE
HARBOR HEIGHTS VIOLATIONS | HIGH | Violations were issued for deliberately ignoring the Order. The applicants attempt to install utilities contrary to the approved plan were stopped by the Village. State officials and attorneys were notified of this conduct. The project is now shut down until proper procedure is followed. | COMPLETE
SEWER /WATER ORDINANCE REVIEW | HIGH | Engineers have completed their drafts and the Ordinances have been sent to the Attorney for review. | IN PROGRESS
ELM STREET LINE PAINTING | MEDIUM | Pricing line paint for Elm Street. | INITIATED
SUTTON PARK FENCE | MEDIUM | We will be installing a fence on the property line between Sutton Park and Suttons Bay Cottages due to the continual violations by renters parking on the park lawn. Surveyor notified. | INITIATED
MASTER PLAN SURVEY | MEDIUM | The survey has been provided to the consultant for review and comment. | COMPLETE
DOWNTOWN BUSINESS SURVEY | MEDIUM | This was made a part of the Master Plan survey. | COMPLETE
MARINA MASTER PLAN REVIEW | MEDIUM | The review has determined that the plan should be updated. We have budgeted for the Plan to be updated in 2023 by a consultant. | COMPLETE
RAINGARDEN RECLAMATION | MEDIUM | Scheduling raingarden vegetation removal and filing. Broadway raingarden removal postponed until 2023 due to unscheduled issues and emergencies. | POSTPONED
NORTH PARK LAUNCH PAYMENT | MEDIUM | Staffing of N. Park no longer a consideration. | COMPLETE
FLAG POLE | MEDIUM | Pricing flag pole for the Village Hall | INITIATED
CONSUMERS ENERGY STREET LIGHT PILOT PROGRAM | MEDIUM | The Village is participating in a dimmable light pilot program. | IN PROGRESS
PLOW TRUCK | MEDIUM | Used truck purchased. | COMPLETE
PLOW TRUCK WING | MEDIUM | Available yet not a necessary purchase at this time. | COMPLETE
NEW LOADER PURCHASE | MEDIUM | The loader has been ordered (2-23-22).The loader was delivered 11-26-22. | COMPLETE
MARINA BRIDGE REPLACEMENT | MEDIUM | Engineer review recommends advanced system for pedestrian bridge. Cost comparison with other similar new bridges are being explored. (10-18-22). | IN PROGRESS
MARINA BEACH MOBI-MAT EXPANSION | MEDIUM | Expansion of ADA beach area will be expanded by purchasing 2 additional mats (5x35) Installed 6-30-22. | COMPLETE
WALL MOUNTED WATER BOTTLE FILERS | MEDIUM | Researching 4 water fountains with bottle filler. | IN PROGRESS
SUTTONS PARK WALKWAY | MEDIUM | We are seeking an estimate for a concrete walking path through the park for installation. This was budgeted for 2022, however, a lack of contractor interest and the waterwheel incident has postponed this improvement. We will move forward with this in 2023. We now feel that we have a reliable concrete contractor. | POSTPONED
FEMA - FIRM MAPS | MEDIUM / LOW | The review period for the new FEMA Flood Insurance Rate Maps (FIRM) ends on March 30th. Following the review period, the FIRM will automatically be considered adopted and in full affect. | COMPLETE
ELM STREET WEIGHT RATING | MEDIUM / LOW | Investigation on the procedure to evaluate and adjust the weight rating on Elm Street has been initiated. This will limit truck traffic on Elm to preserve our infrastructure. | INITIATED
S. SHORE DRIVE EVALUATION | MEDIUM / LOW | Phase #1 Richter/Shore intersection. Upon evaluation, this has been budgeted for 2023. | COMPLETE
VIKING CRUISE LINES | MEDIUM / LOW | Discussions have reopened regarding this initiative. Some negotiations are ongoing to determine benefits vs cost. | COMPLETE
TEMPORARY MOWING SERVICES | MEDIUM / LOW | A brief study was performed to understand if we could offset various time-consuming tasks. The intent of this is to free up DPW time to perform services better suited to their skill set and save the Village $$$. We are moving forward with this initiative. | COMPLETE
DOWNTOWN CAMERAS | MEDIUM / LOW | Cameras will be located at all crosswalks. | POSTPONED
STREET TREES | MEDIUM / LOW | Street tree Spring order placed all trees installed as of 6-30-22. Street trees budgeted for 2023. | COMPLETE
CHERRYLAND FRANCHISE AGREEMENT | MEDIUM / LOW | A new non-exclusive franchise agreement Adopted 3-21-22. | COMPLETE
ICE RINK PARK AGREEMENT | MEDIUM / LOW | A new contract agreement is in place with the Township. | COMPLETE
SAIL SHADE INSTALLATION | MEDIUM / LOW | The DPW has been preparing poles etc. for the installation of the sail. | IDLE
OVERNIGHT PARKING ON PUBLIC STREETS | MEDIUM / LOW | A review of current ordinances will begin to determine if a more strict overnight parking ordinance should be implemented. | INITIATIVE RETRACTED
NATIVE AMERICAN EDUCATIONAL SIGN PROJECT | MEDIUM / LOW | Discussions are taking place to allow educational signs at our parks. Meetings have been very productive. | IDLE
WATERWHEEL EVALUATION | MEDIUM / LOW | A contract for consideration was provided to the VC 6-20-22 meeting. Contract signed and executed on 6-21-22. Initiative changed - see high level priority above titled Waterwheel Sinkhole. | COMPLETE
KEY FOB DIGITAL ENTRANCE | MEDIUM / LOW | We initiated pricing a digital key fob entrance system to determine if it is a logical next step to security of the Administration and DPW offices. The key fob system would replace all the keys that have been distributed since 2017. | INITIATED
INLAND SEAS | MEDIUM / LOW | Discussions on educational sign project, pavilion initiative, campus extension, pedestrian bridge and expanding partnership was very productive and informative. Pavilion initiative voted down 4-3. | COMPLETE
CHERRY CAPITAL CYCLING GRANT | LOW | A grant has been received to purchase a new bicycle fix/work station and an order placed. | COMPLETE
PROPERTY ACQUISITION REQUESTS | LOW | Continuous requests to obtain Village property for private use to be sent to committee/VC for direction. See VSB-Report 2022-25. No property for sale. | COMPLETE
MSUE GARDNER PROGRAM - PARTNERSHIP INITIATIVE | LOW | MSUE Master Gardener program - Projects identified - Implementation postponed due to C-19. | INITIATIVE RETRACTED
M-22 SIDEWALKS | LOW | Met with MDOT on June 15, 2022. Non-motorized map created and provided to MDOT & consultant- - Follow up discussion held on 7-23-22 - more to come… | IN PROGRESS
PEDESTRIAN LIGHT (MDOT) | LOW | Met with MDOT on June 15, 2022. Safety Meeting to discuss M22 design and crossing was productive. | IN PROGRESS
CHARTER FRANCHISE AGREEMENT | LOW | Approved at VC meeting 11-21-2022 | COMPLETE
ELMER'S PAVING PROJECTS | LOW | Tentative projects selected for 2023. S.Shore low spot improvement/Possible St. Mary's drainage/ on street parking issue. Others being evaluated. | COMPLETE
ELECTRIC VEHICLE CHARGING STATIONS | LOW | We have begun efforts on gathering information on granting, costs, etc. | INITIATED
ELECTRIC BOAT CHARGING STATIONS | LOW | We have been contacted regarding the installation of electric boat charging stations. We are in the fact finding stage. Not enough demand to justify installation at this time. | COMPLETE
RAINGARDEN PLANTS | LOW | Raingarden vegetation for M-22 has been ordered 4-25-22. Received and planted. | COMPLETE
STREET LIGHT DISCUSSION | LOW | Broadway Street light to be eliminated. | COMPLETE
VILLAGE HALL CAMERA GRANT | LOW | We are applying for a camera grant to place cameras at the outdoor entrance of the Village Hall. A resolution will be before the VC in November to support the grant request. | COMPLETE

## 2023
PROJECT | PRIORITY LEVEL | DESCRIPTION | STATUS
MASTER PLAN | HIGH | A joint meeting on the Master Plan between PC/VC took place. Minor changes forthcoming. Master Plan changes are being made to address VC concerns. | IN PROGRESS
WATERWHEEL SINKHOLE | HIGH | Re-routed in temporary liner. | COMPLETE
WATERWHEEL CREEK RESTORATION | HIGH | A meeting with Staff, GEI & Kal excavating took place to begin planning implementation. EGLE public review session complete. EGLE permit issued. | IN PROGRESS
INFRASTRUCTURE STUDIES | HIGH | We continue to evaluate our water/sewer availability. Studies and evaluations have been consistent over the past several months. In 2022, the Village was recognized by the State for the progress we have made with our studies. | IN PROGRESS
RATE STUDY | HIGH | Rate analysis for H2O / sewer system received & being analyzed. This has been temporarily halted due to cost. | IDLE
WATER & SERVICE LINE REPLACEMENT | HIGH | The Village Council (6-20-23) approved a contract with F&V to move forward with a study and application for a USDA loan (St.Marys). | IN PROGRESS
WATER RESERVOIR INITIATIVE | HIGH | This was State mandated. The village has not qualified for grants. This initiative is on going. | IN PROGRESS
EGLE ORDERED TRAP BAG REMOVAL | HIGH | In 2019, we received a permit to use a new sand bag product to stop the rapid erosion of the Coal Dock park. EGLE has now begun their removal initiative and ordered the removal of our erosion control. Discussions for an extension and onsite meeting are taking place. | IN PROGRESS
2% GRANT CONSIDERATION | HIGH | Unsuccessful on pre-granting discussions. Moving on…. | COMPLETE
MARINA ORDINANCE UPDATE | HIGH | Review and research continues…. | IN PROGRESS
MARINA MASTER PLAN UPDATE | HIGH | A contract has been signed to update the plan. | IN PROGRESS
PARKS & RECREATION PLAN | HIGH | The Plan was sent to the State for consideration and has been approved. | COMPLETE
DPW GATED ENTRANCE AND SECURITY | HIGH | Northern entrance - Easement language is being reviewed. Elimination, modification or otherwise will be necessary to gate the entrance in 2023. | IN PROGRESS
COURT CASE ZBA APPEAL | HIGH | Michael Sanocki (379 South Shore Drive) has filed an appeal with the Circuit Court against the Village to overturn a ZBA decision. There should be no discussion regarding this appeal. Scheduled for 8-28-2023. The Judge heard arguments and we are awaiting a written verdict. | IN PROGRESS
ELM STREET 3-WAY STOP PROJECT | HIGH | Report received. No 3-way stop in 2023 | COMPLETE
BAYVIEW /LEELANAU HILLS PUD | HIGH | The Roth family has hired a new attorney following the previous attorney stepping down from the case. There should be no discussion on any topic regarding this project. Stay tuned…. | IDLE
CATEGORY "B' ROAD GRANT | HIGH | A 50 % grant request has been submitted ($40,000) to fix 750 ft of Elm Street. Applicants will be notified by mid-September. | COMPLETE
PERSONNEL POLICY AMENDMENTS | HIGH | Modification / Amendments to the Personnel Policy manual have been recommended to the VC for consideration at their 3-20-23 meeting. Approved. | COMPLETE
RESTAURANT v NON-PROFIT | HIGH | The village has unfortunately been dragged into a time consuming disagreement/battle that has escalated into litigious threats. ( Inland Seas v Boones ). A temporary agreement is in place however a solution is not. We will not participate any longer in a solution or get involved in the dispute. | COMPLETE
SEWER /WATER ORDINANCE REVIEW | HIGH | This initiative is moving forward and hoping for a 2023 adoption. | IN PROGRESS
MARINA SLIP POLICY | HIGH | A new marina slip policy has been drafted for consideration / adopted at the 7-17-23 VC Mtg | COMPLETE
SEWER PATCHING FRONT STREET | HIGH | We have exhausted our 2023 budgeted amount of $20,000 for sewer patching. A budget amendment to address further issues may be considered further along in the fiscal year. | COMPLETE
SEWER LINING FRONT STREET | HIGH | Contract Signed 8-22-23. Work to begin after Labor Day. | IN PROGRESS
SEWER CAPACITY | MEDIUM | This is ongoing - data will be presented to the committee and VC for direction once evaluated. | IN PROGRESS
INTERGOVERNMENTAL DISCUSSIONS | MEDIUM | Discussions have been productive and a 3rd draft (August 22, 2023) has been provide to the Twp. supervisor for comment. | IN PROGRESS
LINCOLN / GROVE SIDEWALK REPLACEMENT | MEDIUM | Sidewalk replacement initiative to begin 7-17-23 with the removal of sidewalk by staff. Sidewalks to be formed and complete by 7-21-23. | COMPLETE
PEDESTRIAN LIGHT (MDOT) | MEDIUM | M22 design and crossing discussed with MDOT. | IN PROGRESS
VILLAGE SIGN INITIATIVE | MEDIUM | Village entrance sign/ Marina Park/ Sutton Park have all been installed. | COMPLETE
DDA 2023 CONSULTANT | MEDIUM | A training was held for DDA members to understand their role and abilities. A joint meeting with the VC is forthcoming on September 13th. Following this meeting we will discuss a consultant taking over the DDA. | IN PROGRESS
DIGITAL BATHROOM LOCKS | MEDIUM | Digital locks for Duester & Marina Park bathrooms are being scheduled for installation. The locks are now installed. | COMPLETE
ELM STREET LINE PAINTING | MEDIUM | We have a verbal agreement to have road lines painted on Elm _DELAYED_. | IN PROGRESS
ELM STREET CROSSWALKS | MEDIUM | Crosswalks will be painted by Staff prior to school starting. | COMPLETE
SUTTON PARK FENCE | MEDIUM | We will be installing a fence on the property line between Sutton Park and Suttons Bay Cottages due to the continual violations by renters parking on the park lawn. Surveyor notified. | IN PROGRESS
HARBOR HEIGHTS | MEDIUM | The project is progressing as anticipated. | IN PROGRESS
COMMUNITY BUILDOUT PLAN | MEDIUM | A proposal is forthcoming to the VC (May) to begin the process of understanding density and capacity within our village jurisdiction. The VC has accepted the proposal. | IN PROGRESS
MARINA ELECTRICAL EVALUATION | MEDIUM | We are evaluating the electrical situation for possible improvements/relocation. Electrical has been installed. | COMPLETE
S.SHORE DRIVE IMPROVEMENT | MEDIUM | 2023 Project to begin Spring/Summer. This will address a slumped area of the roadway and include raising a manhole also. Project to begin on 8-23-23 | COMPLETE
BROADWAY/FRONT STREET PATCHING | MEDIUM | Patching due to the filling of raingardens and sewer work will be completed as part of the S.Shore project to avoid exuberant mobilization fees for two separate jobs. | COMPLETE
WATER BILLING EVALUATION | MEDIUM | An evaluation on how we are billing our residents for water is essential to understand if it accurately reflects usage. This is something we hope to initiate sometime in 2023. | IDLE
FLAG POLE | MEDIUM | Pricing flag pole for the Village Hall | INITIATED
ST MARY'S ROAD PROJECT | MEDIUM | Temporary measures will take place however, no final decision on this area will be made in 2023. This area will be evaluated when the waterline is replaced. | IN PROGRESS
GROVE STREET PROJECT | MEDIUM | Initial costs were received however, we are revisiting the total reconstruction of the street to consider alternative solutions and pricing opportunities. | IN PROGRESS
CONSUMERS ENERGY STREET LIGHT PILOT PROGRAM | MEDIUM | The Village is participating in a dimmable street light pilot program. | COMPLETE
MARINA BRIDGE COST ESTIMATES | MEDIUM | Cost Estimate Received - $145,000 Pre-Fab bridge - Helical Piers/Sheet pile etc. $118,600 - Additional cost - Mobilization/oversight/restoration/ sidewalks/ contingencies etc. - $136,500. | INITIATIVE POSTPONED
WALL MOUNTED WATER BOTTLE FILERS | MEDIUM | An ADA compliant water bottle filler / fountain has been installed at N. Park. | COMPLETE
SUTTONS PARK WALKWAY | MEDIUM | The cost to complete a paved ADA compliant walkway and display area is estimated at approximately $40,000. Due to the cost, this will be postponed until waterwheel is completed. Postponed until 2024. | INITIATIVE POSTPONED
DOWNTOWN CAMERAS | MEDIUM / LOW | Stay Tuned…. | IDLE
CONSUMERS ENERGY GRANT | MEDIUM / LOW | Educational Park/ Interpretative Signs / Coal Dock - -The Village did not qualify as administrators felt an educational park did not meet their intent of bringing people together. | COMPLETE
SUTTONS BAY RELEAF PARTNERSHIP | MEDIUM / LOW | Staff finalizing the agreement with planting to occur in October. N. Park farmers market perimeter is the target area. | IN PROGRESS
STREET TREE ORDER | MEDIUM / LOW | We continue our street tree replacement initiative. | IN PROGRESS
SAIL SHADE INSTALLATION | MEDIUM / LOW | The DPW has been preparing poles etc. for the installation of the sail. | IDLE
OVERNIGHT PARKING ON PUBLIC STREETS | MEDIUM / LOW | A review of current ordinances will begin to determine if a more strict overnight parking ordinance should be implemented. | INITIATED
NATIVE AMERICAN EDUCATIONAL SIGN APPROVAL | MEDIUM / LOW | Discussions are taking place to allow educational signs at our parks. The Committee recommended the project to the village council for consideration. Presentation by Emily Modrell before VC on March 20, 2023. APPROVED. Letter sent. | COMPLETE
KEY FOB DIGITAL ENTRANCE | MEDIUM / LOW | We initiated pricing a digital key fob entrance system to determine if it is a logical next step to security of the Administration and DPW offices. The key fob system would replace all the keys that have been distributed since 2017. | IDLE
VILLAGE HALL EXTERIOR LIGHT IMPROVEMENT | LOW | The Village Hall exterior lights are set on a timer. We are looking into a modification to incorporate an "eye" to save $$$. | IDLE
M-22 SIDEWALKS | LOW | Non-motorized map created and provided to MDOT & consultant- more to come… | IN PROGRESS
PEDESTRIAN LIGHT (MDOT) | LOW | Safety Meeting to discuss M22 design and crossing was productive. Stay tuned…. | IN PROGRESS
ELECTRIC VEHICLE CHARGING STATIONS | LOW | Stay Tuned…. | IDLE
VILLAGE HALL CAMERA GRANT | LOW | Grant Requested - Following numerous successful grants we were denied this funding cycle. | COMPLETE
RAINGARDEN PLANTS | LOW | Raingarden vegetation for two M-22 raingardens are being discussed. | IN PROGRESS
RAINGARDENS - GENERAL | LOW | Various individuals, council members and Green Suttons Bay have been active with maintaining the raingardens. | IN PROGRESS
CHERRY CAPITAL CYCLING GRANT | LOW | We are contemplating application for another grant. Successful in 2022. | INITIATIVE RETRACTED
DOWNTOWN LIGHT POLE IMPROVEMENTS | LOW | Upgrading the current light poles has been researched. They should be taller and have a uniform size for banners rather than a unique size that costs significantly more. | INITIATED